## Cover
Zain Jordan
RAID - Wangiri Fraud- System Test Cases

## Execution Report
OVERALL TEST CASE STATUS |  |  | OVERALL DEFECT STATUS |  |  |  | OVERALL "OPEN" DEFECTS (i.e. New, Under Analysis, Working, Reopen) |  |  | Defect classification type (i.e. Product Type" or "Implementation Type)
CASE STATUS | NR | % | DEFECT STATUS | NR | % | NOTE | DEFECT PRIORITY | NR | % | DEFECT TYPIFICATION | NR | %
NOT STARTED | 10 | 35.71% | NEW | 2 | 100% | New issue raised | HIGH | 2 | 100% | Product Type | 0 | 0%
IN PROGRESS | 0 | 0% | UNDER ANALYSIS | 0 | 0% | Issue being analysed | MEDIUM | 0 | 0% | Implementation type | 2 | 100%
OK | 13 | 46.43% | WORKING | 0 | 0% | Fixing defect | LOW | 0 | 0%
NOK | 5 | 17.86% | REOPEN | 0 | 0% | Failed in retest
|  |  | POSTPONED | 0 | 0% | To be evaluated later | Service Impact | 0 | 0%
|  |  | REJECTED | 0 | 0% | Issue was rejected | No Service Impact | 0 | 0%
|  |  | FIXED | 0 | 0% | Ready for retest
|  |  | CLOSED | 0 | 0% | Retested OK
TOTAL | 28 | 100% | TOTAL | 2 | 100% |  | TOTAL | 2 | 100% | TOTAL | 2 | 100%

## Test Cycle Plan
TEST CYCLE | STEP NUMBER | STEP DESCRIPTION | INPUT DATA | EXPECTED RESULT | ACTUAL STEP RESULT | TEST CASE STATUS | CATEGORY | ASSIGNED_TO | START DATE | END DATE | NR. OF EXECUTIONS | COMPLETE SUCCESSFULLY % | NOTES
Portal
TestID | U1 |  |  |  |  | OK | Portal
TestDescription | User Management
RequirementID
Test Preconditions | User should be able to login/logout to the RAID system
| 1 | Login with your username and password |  | User should be successfully logged in. | User is able to login to the portal with username and password.
| 2 | Click on the top right menu, select the "Sites & Pages" and select "Fraud Management" site |  | Fraud Management site home page should be visible. | User is able to see the fraud management site
| 3 | Click on the "Sign Out" option located next to the "Manage Account" option at the bottom left corner of the side menu. |  | User should be redirected to the login page after clicking on the "Sign Out" option | User is getting redirected to login page once the user click on the sign out option
TestID | P1 |  |  |  |  | OK | Portal
TestDescription | Portal Navigation
RequirementID
Test Preconditions | User should be able to see the portal tree
| 1 | Fllowing links should be available in the left side menu BUSINESS OVERVIEW INBOX FRAUD MANAGEMENT Fraud Center Rules Management Rules Lists Engine Management Console INVESTIGATION CENTER Ad Hoc Queries Global Data search FINANCIAL REPORTS Fraud Amounts Fraud Loss BUSINESS STATISTICS Case Statistics Cases overview Cases reclassification Case events recovery Efficiency Analyst Statistics Team performance SLA Overview Rule Statistics Overview Effectiveness Performance Fraud Rule Optimizer Analysis OPERATIONAL REPORTS System Auditing Semaphore Control SYSTEM PARAMETERS Business Operational SETTINGS TOOLBOX Configuration Operational |  | User should be able to see links and sub links while hovering the mouse on the left side menu | User is able to see all required links in the portal.
User should be able to click on the links
TestID | P2 |  |  |  |  | OK | Portal
TestDescription | Portal Navigation
RequirementID
Test Preconditions | User should be able to see the online help
| 1 | Click on the online help button (?) on the top right side of the screen |  | User should be able to see the hyper links to the pages that contains the searched text | User us able to see the hyper link that contains the searched text.
| 2 | provide any text(E.g. "Loading" or "Lookups" etc ) and press enter |  | On click on these hyperlinks, the user should be redirected to online help pages | On click on the hyper links, the user is able to see the detailed information
Loadings
TestID | L1 |  |  |  |  | OK | Loading
TestDescription | Loading :: Zain Ctrl LD MSC Eric -VOICE/SMS Evt Prs
RequirementID | Pre process Ericssion raw file.
Test Preconditions | Files are located in the input directories
| 1 | Execute Control Loading Flow (Zain Ctrl LD MSC Eric -VOICE/SMS Evt Prs) to do pre parsing | Sample files | No errors occured during execution
| 2 | Validate target directories have correct output: /appsdata/rafm_data/data/loading/msc/in /appsdata/rafm_data/data/loading/smsc/in |  | Files exist on target directories and have correct format and output
TestID | L2 |  |  |  |  | NOK | Loading
TestDescription | Loading :: WDT Ctrl LD MSC
RequirementID | Enrichment of Voice Events.
Test Preconditions | Files are located in the input directories
| 1 | Execute Control Loading Flow (WDT Ctrl LD MSC) to do loading for Voice Events. | Sample files | No errors occured during execution | No errors observed during the execution
| 2 | Validate the processed files are moved to the below folder: /appsdata/rafm_data/data/loading/msc/out |  | Processed files should be moved to out directory | Processed files moved to out dir
| 3 | Validate target directories have correct output for Detection flows /appsdata/rafm_data/datafms/detection/subscribers/events/in/ /appsdata/rafm_data/datafms/detection/offnet_subscribers/events/in/ |  | Files exist on target directories and have correct format and output, Detection files generated by MSC loading flow should start with DET_MSC_. File should be compressed. | Files existing on target directory
| 4 | Navigate to Ad hoc queries and apply filter to fetch processed record. |  | Processed record should be visible. | processed records are available in IWB
| 5 | Navigate to Global Data search (data section). |  | Processed record should be visible.
| 6 | Check for the validity of failed events for the file processed. |  | Only Valid rejections should be there.
TestID | L3 |  |  |  |  | NOK | Loading
TestDescription | Loading :: WDT Ctrl LD SMSC
RequirementID | Enrichment of SMS Events.
Test Preconditions | Files are located in the input directories
m | 1 | Execute Control Loading Flow (WDT Ctrl LD SMSC) to do loading for Voice Events. | Sample files | No errors occured during execution | No error observed
| 2 | Validate the processed files are moved to the below folder: /appsdata/rafm_data/data/loading/smsc/out |  | Processed files should be moved to out directory | files moved to out directory
| 3 | Validate target directories have correct output for Detection flows. /appsdata/rafm_data/datafms/detection/subscribers/events/in/ /appsdata/rafm_data/datafms/detection/offnet_subscribers/events/in/ |  | Files exist on target directories Detection files generated by SMSC loading flow should start with DET_SMSC_.
| 4 | Navigate to Ad hoc queries and apply filter to fetch processed record. |  | Processed records should be visible.
| 5 | Navigate to Global Data search (data section). |  | Processed records should be visible.
| 6 | Check for the validity of failed events for the file processed. |  | Only Valid rejections should be there.
Detection
TestID | Det1 |  |  |  |  | OK | ACM
TestDescription | ACM : Alert Generation
RequirementID | Case generation
Test Preconditions | Relevant input data/hotlist/reference data/Rules should be present.
| 1 | Validate if Alerts are getting generated for WDT Ctrl DET Eval Offnet Subscribers. |  | 1. Flow should be completed successfully 2. New alerts generated by the engine should be available in the "Business Statistics" -> "Rule Statistics" -> "Overview" -> "Detection Rules" 3. User should be able to filter the alerts based on the "Engine Name" and "Rule Name" | Flow completed without any issues and alerts generated properly
| 2 | Verify input files for Alarm generation in the below given folder. /appsdata/rafm_data/datafms/correlation/offnet_subscriber/in/1/ |  | A file should be generated in the correlation flow input folder for the alarm generation | Delta file generated and the alarms also generated
TestID | Det2 |  |  |  |  | Not Started | ACM
TestDescription | ACM : Alert Generation
RequirementID | Case generation
Test Preconditions | Relevant input data/hotlist/reference data/Rules should be present.
| 1 | Validate if Alerts are getting generated for WDT DET IRSF HL BNum Offnet Subscribers. |  | 1. Flow should be completed successfully 2. New alerts generated by the engine should be available in the "Business Statistics" -> "Rule Statistics" -> "Overview" -> "Detection Rules" 3. User should be able to filter the alerts based on the "Engine Name" and "Rule Name"
| 2 | Verify input files for Alarm generation in the below given folder. /appsdata/rafm_data/datafms/correlation/offnet_subscriber/in/1/ |  | A file should be generated in the correlation flow input folder for the alarm generation
TestID | Det3 |  |  |  |  | Not Started | ACM
TestDescription | ACM : Alert Generation
RequirementID | Case generation
Test Preconditions | Relevant input data/hotlist/reference data/Rules should be present.
| 1 | Validate if Alerts are getting generated by WDT Ctrl DET IRSF HL BNum Subscribers |  | 1. Flow should be completed successfully 2. New alerts generated by the engine should be available in the "Business Statistics" -> "Rule Statistics" -> "Overview" -> "Detection Rules" 3. User should be able to filter the alerts based on the "Engine Name" and "Rule Name"
| 2 | Verify input files for Alarm generation in the below given folder. /appsdata/rafm_data/datafms/correlation/subscriber/in/1/ |  | A file should be generated in the correlation flow input folder for the alarm generation
TestID | Det4 |  |  |  |  | Not Started | ACM
TestDescription | ACM : Alert Generation
RequirementID | Case generation
Test Preconditions | Relevant input data/hotlist/reference data/Rules should be present.
| 1 | Validate if Alerts are getting generated by WDT Ctrl DET IRSF HL Subscribers |  | 1. Flow should be completed successfully 2. New alerts generated by the engine should be available in the "Business Statistics" -> "Rule Statistics" -> "Overview" -> "Detection Rules" 3. User should be able to filter the alerts based on the "Engine Name" and "Rule Name"
| 1 | Verify input files for Alarm generation in the below given folder. /appsdata/rafm_data/datafms/correlation/subscriber/in/1/ |  | A file should be generated in the correlation flow input folder for the alarm generation
TestID | Det5 |  |  |  |  | Not Started | ACM
TestDescription | ACM : Alert Generation
RequirementID | Case generation
Test Preconditions | Relevant input data/hotlist/reference data should be present.
| 1 | Validate if Alerts are getting generated by WDT Ctrl DET IRSF HU Offnet Int |  | 1. Flow should be completed successfully 2. New alerts generated by the engine should be available in the "Business Statistics" -> "Rule Statistics" -> "Overview" -> "Detection Rules" 3. User should be able to filter the alerts based on the "Engine Name" and "Rule Name"
| 1 | Verify input files for Alarm generation in the below given folder. /appsdata/rafm_data/datafms/correlation/offnet_subscriber/in/1/ |  | A file should be generated in the correlation flow input folder for the alarm generation
Correlation
TestID | Cor1 |  |  |  |  | Not Started | ACM
TestDescription | ACM : Alarm Generation
RequirementID | Case generation
Test Preconditions | Alert should be generated and delta file should be present in the correlation input folder.
| 1 | Validate if Alarms are getting generated by WDT Ctrl COR Subscribers. |  | 1. Flow should be completed successfully 2. New alerts generated by the engine should be available in the "Business Statistics" -> "Rule Statistics" -> "Overview" -> "Correlation Rules" 3. User should be able to filter the alerts based on the "Engine Name" and "Rule Name"
TestID | Cor2 |  |  |  |  | OK | ACM
TestDescription | ACM : Alarm Generation
RequirementID | Case generation
Test Preconditions | Alert should be generated and delta file should be present in the correlation input folder.
| 1 | Validate if Alarms are getting generated by WDT Ctrl COR Offnet Subscriber. |  | 1. Flow should be completed successfully 2. New alerts generated by the engine should be available in the "Business Statistics" -> "Rule Statistics" -> "Overview" -> "Correlation Rules" 3. User should be able to filter the alerts based on the "Engine Name" and "Rule Name" | COR Offnet engine is able to generate alarms
Reporting
TestID | Dsh1 |  |  |  |  | OK | Dashboard
TestDescription | Dashboard::Inbox
RequirementID | Check Dashboard Content
Test Preconditions | Cases should be available.
| 1 | select "Inbox" from left side menu |  | User should be able to click on the "Inbox"
| 2 | Validate all the filters are working as per expectation. |  | Not expected to have error messages on the screen. Filter should successfully apply.
| 3 | Validate actions like claim-assign and discard is working. |  | User should be able to claim, assign and discard cases
TestID | Dsh2 |  |  |  |  | OK | Dashboard
TestDescription | Dashboard::Inbox - Cases
RequirementID | Check Dashboard Content
Test Preconditions | Cases should be available.
| 1 | select "Inbox" from left side menu and click on "View Case" |  | User should be able to click on the "Inbox" User should be able to view the selected case content | User is able to view the content of the case
| 2 | Validate alarm timeline is according to the alarm generated |  | Not expected to have error messages on the screen. | alarms and alerts are displaying in the case
| 3 | Validate participating records are according to the alert generated. |  | Participated record information should be displayed in the inbox page
TestID | Dsh3 |  |  |  |  | NOK | Dashboard
TestDescription | Dashboard::Inbox - Cases Actions
RequirementID | Check Dashboard Content
Test Preconditions | Case should be claimed/assigned to the user
| 1 | select "Inbox" from left side menu and click on "Analyse Case". |  | User should be able to open the case which is assigned to him or should be able to claim a case with status "New". | Some of the fields are disabled in the case decision dashboard which need to be filled while closing the case. It was disabled as part of the demo.
| 1 | Closed Case as Fraud. |  | User should be able to close case as Fraud User should be able to enter prevented amount, recovered amount, loss amount while closing the case Closed case information should be available in the inbox - closed case page
| 2 | Closed Case as Non Fraud |  | User should be able to close case as Non-Fraud Closed case information should be available in the inbox - closed case section
TestID | Dsh4 |  |  |  |  | Not Started | Dashboard
TestDescription | Dashboard::Inbox - Cases Actions to VPE
RequirementID | Send for VPE for block
Test Preconditions | Case should be claimed/assigned to the user
| 1 | select "Inbox" from left side menu and click on "Analyse Case". |  | User should be able to open the case which is assigned to him and under status "Under Analysis"
| 1 | Click on "Send VPE" Action for blocking the number in voice firewall. |  | 1. A file should be generated in the SFTP folder of VPE block. 2. File should be in the required format which is discussed with VPE team.
TestID | Dsh5 |  |  |  |  | OK | Dashboard
TestDescription | Dashboard::Investigation Center >> Global Data Search
RequirementID | Check Dashboard Content
Test Preconditions | Test case L1, L2 and L3 should be completed
| 1 | Login to Portal and navigate to Investigation Center >> Global Data Search - Search Events for a particular MSISDN -Validate datalist data on " Voice", "SMS" Events - Change the date and verify the user is able to fetch the events for different dates. |  | Not expected to have error messages on the screen. Filter should successfully apply. User should be able to export the data. User should be able to change the date using date widget. | User is able to fetch the records with a single msisdn using this page. No error observed
TestID | Dsh6 |  |  |  |  | OK | Dashboard
TestDescription | Dashboard::Investigation Center >> Ad Hoc Queries
RequirementID | Check Dashboard Content
Test Preconditions | Test case L1, L2 and L3 should be completed
| 1 | Login to Portal and navigate to Investigation Center >> Ad Hoc Queries - Search Events for a particular MSISDN -Validate datalist data on " Voice", "SMS" Events |  | Not expected to have error messages on the screen. Filter should successfully apply. User should be able to export the data in CSV/Excel format. | User is able to execute adhoc queries and fetch the data properly
TestID | Dsh7 |  |  |  |  | OK | Dashboard
TestDescription | Dashboard:: Fraud Management >> Fraud Center > Hotlists
RequirementID | Check Dashboard Content
Test Preconditions | User should be able to access the RAID GUI and Fraud Administrator site.
| 1 | Go to Fraud Management >> Fraud Center > Hotlists - Create , Update and delete entry in Hotlist. for example, "Wangiri Numbers" |  | Not expected to have error messages on the screen. User should be able to add/update/delete the hotlists entries | User is able to see all hotlists available in the system User is able to create new hotlist user is able manipulate the data in the hotlists
TestID | Dsh8 |  |  |  |  | OK | Dashboard
TestDescription | Dashboard:: Fraud Management >> Rule Management
RequirementID | Check Dashboard Content
Test Preconditions | Engines should be created and added in engine tree
| 1 | Go to Fraud Management >> Rule Managment - Create , Update and delete a new/existing rule. |  | Not expected to have error messages on the screen. user should be create/modify/delete existing rules. user should be able to activiate/deactivate existing rules user should be able to use the hotlists in the rules | User is able to perform all the actions such as modify, edit, create and debug of the rules.
TestID | Dsh9 |  |  |  |  | NOK | Dashboard
TestDescription | Dashboard::Operational Reports >> System Auditing
RequirementID | Check Dashboard Content
Test Preconditions | Test case related to Loading and Detection should be completed
| 1 | Go to Operational Reports >> System Auditing and verify the data available in the report. |  | System auditing dashboard should display the details if any execution is in error for following types 1. Loading 2. Detection 3. Correlation 4. Housekeeping Verify the indicators displayed in the dashboard. | System auditing flow is in error
TestID | Dsh10 |  |  |  |  | Not Started | Dashboard
TestDescription | Dashboard:: Financial Reports >> Fraud Amount
RequirementID | Check Dashboard Content
Test Preconditions | Atleast one case should be closed as "Fraud"
| 1 | Go to Financial Reports >> Fraud Amount - Check for various indicators. |  | Not expected to have error messages on the screen. Filter should successfully apply.
TestID | Dsh11 |  |  |  |  | Not Started | Dashboard
TestDescription | Dashboard:: Financial Reports >> Fraud Loss
RequirementID | Check Dashboard Content
Test Preconditions | Atleast one case should be closed as "Fraud"
|  | Go to Financial Reports >> Fraud Loss - Check for various indicators. |  | Not expected to have error messages on the screen. Filter should successfully apply.
TestID | Dsh12 |  |  |  |  | Not Started | Dashboard
TestDescription | Dashboard:: Business Statisitcs >> Cases Statistics > Case Overview
RequirementID | Check Dashboard Content
Test Preconditions | Cases should be there and actions should be taken already.
| 1 | Go to Business Statisitcs >> Cases Statistics > Case Overview - Check for various indicators. |  | Not expected to have error messages on the screen. Indicators available in the dashboard should be upto date. Filter should successfully apply.
TestID | Dsh13 |  |  |  |  | Not Started | Dashboard
TestDescription | Dashboard:: Business Statisitcs >> Rules Statistics > Rule Overview
RequirementID | Check Dashboard Content
Test Preconditions | Cases should be there and actions should be taken already.
| 1 | Go to Business Statisitcs >> Rules Statistics > Rule Overview - Check for various indicators. |  | Not expected to have error messages on the screen. Indicators available in the dashboard should be upto date. Filter should successfully apply.
House Keeping
TestID | HK1 |  |  |  |  | OK | Dashboard
TestDescription | Housekeeping :: WDT HK Database
RequirementID
Test Preconditions | DB tables should have data
| 1 | Execute Housekeeping Flow (WDT HK Database) |  | Flow instance should get completed succesfully.
| 2 | Data on the tables should get cleared based on the HK configuration in the reference data WDT Ref Housekeeping Management" to view the reference data, Navigate to System Parameter -> Operational -> Housekeeping Management -> Search for Database |  | Data older than the configured value (E.g. 30 days) should be deleted for the selected ENTITY | HK Database works with no error
| 3 | Verify the flow execution status from System Auditing -> View statistics -> Other process -> Select "WDT HK Database" and verify the execution status |  | latest execution status should be available in the Auditing dashboard. System auditing data can be refereshed by scheduler for every 5 minute or by clicking manually on the "Refresh Now" button
TestID | HK2 |  |  |  |  | NOK | Dashboard
TestDescription | Housekeeping :: WDT HK Filesystem
RequirementID
Test Preconditions | File directories should have existing files
| 1 | Execute flow WDT HK Filesystem |  | HK file system flow should get completed succesfully
| 2 | Data on the folderes should get cleared based on the HK configuration in the reference data WDT Ref Housekeeping Management" to view the reference data, Navigate to System Parameter -> Operational -> Housekeeping Management -> Seach for DATA_FILES |  | Files older than the configured (E.g. 30 days) should be deleted | Flow gets finished, However it is failing with error " 2025-06-18 20:23:55,906 [.JobManager.Wrk.1136] ERROR wedo.cbpm.task.TaskFileOperation.[Delete Files] JAF_G1000 [] - wedo.jaf.util.IncorrectTypeException: Parameter could not converted into java.util.Date from java.lang.Long -> 1,747,848,233"
| 3 | Verify the flow execution status from System Auditing -> View statistics -> Other process -> Select "WDT HK Filesystem" and verify the execution status |  | latest execution status should be available in the Auditing dashboard. System auditing data can be refereshed by scheduler for every 5 minute or by clicking manually on the "Refresh Now" button
Note on A1: WDT: Test Cycle identifier (test sets with Features Group, or Test Phases…)
Note on B1: WDT: Test Case Step identifier
Note on C1: WDT: Test Case Step description
Note on D1: WDT: Input date(if applicable)
Note on E1: WDT: Sub test case description.
Note on F1: WDT: Actual Step Result
Note on G1: WDT: Status of test case. See on the sheet "Reference" the list of possible status
Note on H1: WDT: Category identifier. e.g Feature Group name, Functional test, Non Functional test..
Note on I1: WDT: Responsible tester
Note on A3: WDT: Test Cycle identifier (test sets with Features Group, or Test Phases…)
Note on B3: WDT: Test Case Step identifier
Note on C3: WDT: Test Case Step description
Note on D3: WDT: Input date(if applicable)
Note on E3: WDT: Sub test case description.
Note on F3: WDT: Actual Step Result
Note on G3: WDT: Actual Step Result
Note on H3: WDT: Category identifier. e.g Feature Group name, Functional test, Non Functional test..
Note on I3: WDT: Responsible tester
Note on L3: WDT: Number of text case execution

## Defects
DEFECT ID | TEST CASE ID/NAME | INITIALIZER | DEFECT DESCRIPTION | PRIORITY | DEFECT TYPIFICATION | COMMENTS / HISTORY | RESOLUTION ACTIONS | RESOLUTION RESPONSIBLE | DEFECT DETECTED ON DATE | ACTUAL RESOLUTION DATE | STATUS | Service Impact
1 | L2 |  | MSC records are getting rejected with following error. 1. an error related to lookup Error executing statement Lookup (name=WDT Tariffs) . Reason: Index DESTINATION_PREFIX for lookup named WDT Tariffs doesnt allow null values at wedo.jaf.smarttransform2.engine.StandardEngine.execute(StandardEngine.java:119) 2. wedo.jaf.cbpm.flow.ProcessErrorException: Error executing task Business Logic due to Error executing statement Set (Flow::VAR_IMEI_LAST_DIGIT = $Right({Flow::VAR_IMEI},1)). Reason: Error while evaluating WEL Expression: [$Right({Flow::VAR_IMEI}, 1)] | High | Implementation type |  |  |  | 17-06-2025 |  | NEW
2 | L3 |  | Number normalization is not properly happening for offnet events B Number: 00962796608074 expected to have without 00 | High | Implementation type |  |  |  | 18-06-2025 |  | NEW
Note on B1: WDT: Test case identifier or Name (Sheet Test Cycle Plan or Test specification Document)
Note on C1: WDT: Detected By ?
Note on D1: WDT: Describing the situation where the problem occurred, to indicate whether the data used. If a document with specification of tests has been developed to identify the test case identifier.
Note on E1: WDT: Priority level for analysis/resolution
Note on F1: WDT: defect typification type: - Product Type - Implementation Type
Note on G1: WDT: Comments
Note on H1: WDT: R&D coments about possible resolution
Note on I1: WDT:Who is assigned the responsibility of the resolution.
Note on L1: WDT: See on the sheet "Reference" the possible status list.

## Enhancement
Enhancement ID | Requirment Summary | Raised By | Requirment Details | PRIORITY | COMMENTS / HISTORY | STATUS | CLOSED BY

## Reference
Priority | Defect Status | Description | Category name | Case Status | Defect Tipification
High | NEW | New issue raised | Loading | NOT STARTED | Product Type
Medium | UNDER ANALYSIS | Issue being analysed | Dashboard | IN PROGRESS | Implementation type
Low | WORKING | Fixing defect | Common Test Case | OK
| REOPEN | Failed in retest | Case Management | NOK
| POSTPONED | To be evaluated later |  | DISCARDED
| REJECTED | Issue was rejected
| FIXED | Ready for retest
| CLOSED | Retested OK

## Changes required
L2 | WDT Ctrl LD MSC
need to check whether the tasks such as DS IMEI, DS ROAMERS /appsdata/rafm_data/datastore/imei/1 - 155 GB
Few records are getting discard because of the B Number format issue. rdr_CALLED_PARTY_NUMBER (String) "119627959641980962795964198" do we need to inform customer or is it some valid scenario
L3
Some times the A NUMBER is not looking correct for SMSMT events. 12397737
Short code related cases need to be cleaned and add a permanent fix to remove the short code related alerts